## Overview
HealthAccess - Stakeholder Status Report
Generated 2026-10-11 17:09 UTC ¦ matdevstamp/inl-3-awesome-journal
Summary
Metric | Planned | Open | Closed | Blocked | Overdue | Unassigned
Count | 18 | 0 | 19 | 0 | 4 | 3
Epics (by Gate)
Epic (Gate) | Tasks | Planned | Open | Closed | Blocked | Overdue | Unassigned | Next deadline
1-Decisions | 3 | 0 | 0 | 3 | 0 | 0 | 2
2-Scaffold | 7 | 0 | 0 | 7 | 0 | 0 | 0
3-Features | 6 | 0 | 0 | 6 | 0 | 0 | 0
4-Integration | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 2026-09-24
5-Delivery | 3 | 0 | 0 | 3 | 0 | 0 | 1
Other | 16 | 16 | 0 | 0 | 0 | 2 | 0 | 2026-10-10
Streams (ownership)
Stream | Tasks | Planned | Open | Closed | Blocked | Overdue | Next deadline
A-Identity | 2 | 0 | 0 | 2 | 0 | 0
B-Patient | 1 | 0 | 0 | 1 | 0 | 0
C-Notes | 1 | 0 | 0 | 1 | 0 | 0
D-Audit | 2 | 0 | 0 | 2 | 0 | 0
Other | 31 | 18 | 0 | 13 | 0 | 4 | 2026-09-24

## Changelog
Changelog - changes since the previous export
Compared against the snapshot of 2026-10-11 16:58 UTC
Sheet | Task | What changed | Before | After
Questions | 13 Patient View & Search | Question added |  | How to handle Polish characters in search? (ł, ż, ó)
Questions | 13 Patient View & Search | Question removed | How to handle Swedish characters in search? (å, ä, ö)
Questions | 17 User Roles & Access Control | Question added |  | How to handle organization-based access for primary care centre? Answered: primary care centre is the login role
Questions | 17 User Roles & Access Control | Question removed | How to handle organization-based access for vårdcentral? Answered: vårdcentral is the login role
Questions | 36 Hackathon Documentation | Question added |  | Remove the course logbooks from the fork; keep `gruppkontrakt.md` and the meeting notes for honest provenance
Questions | 36 Hackathon Documentation | Question removed | Keep `gruppkontrakt.md` and the course logbooks in the fork, or remove them? Leaving them is honest; removing reduces noise

## Tasks
Key | Epic (Gate) | Stream | Title | State | Assignee | Deadline | Effort | Blocked by | Related | GitHub | Open questions
01 | 1-Decisions |  | Project Setup & Group Contract | Closed | Team | 2026-09-04 | 2h |  |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/1 | 4
02 | 1-Decisions |  | Database Choice Discussion | Closed | Team | 2026-09-04 | 1h (meeting) | #1 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/2 | 4
03 | 1-Decisions |  | Ripwire Architecture Artifacts | Closed | Team (Gate 1 — Matias coordinates) | 2026-09-07 | 2h | #1, #2 | #30 | https://github.com/matdevstamp/inl-3-awesome-journal/issues/3 | 1
04 | 2-Scaffold |  | Database Design & Setup | Closed | matdevstamp | 2026-09-07 | 4h | #1, #2, #3 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/4 | 4
05 | 2-Scaffold |  | Next.js + Tailwind CSS + shadcn/ui Setup | Closed | matdevstamp | 2026-09-07 | 3h | #1, #3 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/6 | 3
06 | 2-Scaffold |  | Backend Project Setup (Next.js Route Handlers & Services) | Closed | matdevstamp | 2026-09-07 | 4h | #4, #6 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/7 | 3
07 | 2-Scaffold |  | TypeScript Strict Configuration | Closed | matdevstamp | 2026-09-07 | 2h | #6, #7 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/8 | 3
08 | 2-Scaffold |  | ESLint + Prettier Configuration | Closed | matdevstamp | 2026-09-07 | 2h | #6, #8 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/9 | 3
09 | 2-Scaffold |  | Playwright E2E Testing | Closed | matdevstamp | 2026-09-07 | 8h | #6, #7, #8, #9 | #11, #29 | https://github.com/matdevstamp/inl-3-awesome-journal/issues/10 | 4
10 | 2-Scaffold |  | GitHub Actions CI/CD Workflow | Closed | matdevstamp | 2026-09-07 | 3h | #6, #9, #8, #7 | #10 | https://github.com/matdevstamp/inl-3-awesome-journal/issues/11 | 3
11 | 3-Features | A-Identity | Backend API & Authentication | Closed | Kassim10 | 2026-09-10 | 8h | #4, #8, #7 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/13 | 4
12 | 3-Features | A-Identity | Frontend UI Development | Closed | rcilomba | 2026-09-11 | 12h | #6, #8, #7 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/14 | 4
13 | 3-Features | B-Patient | Patient View & Search | Closed | rcilomba | 2026-09-15 | 6h | #4, #13, #14 | #16 | https://github.com/matdevstamp/inl-3-awesome-journal/issues/15 | 4
14 | 3-Features | C-Notes | Medical Notes with Visibility Control | Closed | Kassim10 (backend visibility) + rcilomba (UI) | 2026-09-22 | 5h | #4, #13, #14 | #15 | https://github.com/matdevstamp/inl-3-awesome-journal/issues/16 | 4
15 | 3-Features | D-Audit | Blockchain Access Logging | Closed | umoraghad0-del (huvudansvar, Stream D) | 2026-09-21 | 8h | #4, #8, #7 | 18 | https://github.com/matdevstamp/inl-3-awesome-journal/issues/17 | 4
16 | 3-Features | D-Audit | P2P Network Implementation | Closed | umoraghad0-del (pair-programmering) | 2026-09-21 | 6h | #17, #7 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/18 | 4
17 | 4-Integration |  | User Roles & Access Control | Planned | rcilomba | 2026-09-24 | 6h | #13, #14, #15, #16 |  |  | 4
18 | 4-Integration |  | Socket.io Broadcasting | Planned | umoraghad0-del (pair-programmering) | 2026-09-28 | 5h | #16, #18, #14, 17 | #17 |  | 4
19 | 5-Delivery |  | Testing & Quality Assurance | Closed | Team | 2026-09-23 | 8h | #17, #18, 17, 18 | #10, #30 | https://github.com/matdevstamp/inl-3-awesome-journal/issues/29 | 4
20 | 5-Delivery |  | Documentation & README | Closed | Kassim10 | 2026-09-29 | 4h | #1 | #3, #29 | https://github.com/matdevstamp/inl-3-awesome-journal/issues/30 | 4
21 | 5-Delivery |  | Presentation Preparation | Closed | Kassim10 | 2026-10-01 | 6h | #29, #10, #30 |  | https://github.com/matdevstamp/inl-3-awesome-journal/issues/31 | 4
22 | Other |  | Solana Repo Split and Toolchain | Planned | matdevstamp | 2026-10-10 | 5h |  | 24 |  | 2
23 | Other |  | Freeze the Interface Contract | Planned | matdevstamp | 2026-10-10 | 3h |  | 24, 25 |  | 2
24 | Other |  | Solana Program Scaffold | Planned | matdevstamp | 2026-10-11 | 4h | 23 | 27 |  | 3
25 | Other |  | Pure Hash Chain Module | Planned | matdevstamp | 2026-10-11 | 5h | 23 | 27 |  | 2
26 | Other |  | Durable Outbox and Solana Flusher | Planned | matdevstamp | 2026-10-12 | 9h | 23 | 32 |  | 3
27 | Other |  | Build the Anchor Program | Planned | matdevstamp | 2026-10-11 | 5h | 24, 25 | 28, 29 |  | 2
28 | Other |  | Devnet Deploy | Planned | matdevstamp | 2026-10-11 | 2h | 27 | 30 |  | 2
29 | Other |  | Solana Program Tests | Planned | matdevstamp | 2026-10-11 | 7h | 27, 28 | 35 |  | 2
30 | Other |  | Solana Client and Environment | Planned | matdevstamp | 2026-10-12 | 5h | 27, 28 | 32 |  | 2
31 | Other |  | Remove the Homemade Blockchain | Planned | matdevstamp | 2026-10-12 | 6h | 30 | 32 |  | 2
32 | Other |  | Wire Flusher to the Solana Program | Planned | matdevstamp | 2026-10-12 | 5h | 31, 30 | 33 |  | 2
33 | Other |  | Patient Wallet Integration | Planned | matdevstamp | 2026-10-12 | 6h | 32 | 34 |  | 2
34 | Other |  | Solana Verification UI | Planned | matdevstamp | 2026-10-12 | 6h | 32 | 33 |  | 2
35 | Other |  | E2E and Submission Disclosure | Planned | matdevstamp | 2026-10-12 | 4h | 29, 32 | 36, 37 |  | 2
36 | Other |  | Hackathon Documentation | Planned | matdevstamp | 2026-10-12 | 5h | 32 | 35, 37 |  | 2
37 | Other |  | Hackathon Submission and Decks | Planned | matdevstamp | 2026-10-13 | 13h | 35, 36 | 32 |  | 3

## Questions
Epic (Gate) | Task | Question | Resolved?
1-Decisions | 01 Project Setup & Group Contract | Frontend: React inside Next.js (fullstack) — decided at kickoff | Yes
1-Decisions | 01 Project Setup & Group Contract | Auth: JWT in an httpOnly cookie — decided at kickoff | Yes
1-Decisions | 01 Project Setup & Group Contract | Blockchain: simple custom chain (stream D split TBD) — decided at kickoff | Yes
1-Decisions | 01 Project Setup & Group Contract | Database: PostgreSQL (dev + prod) — decided at kickoff | Yes
1-Decisions | 02 Database Choice Discussion | Which database do we choose? → **PostgreSQL** (dev and prod) | Yes
1-Decisions | 02 Database Choice Discussion | How to handle the P2P requirement with the chosen database? | Yes
1-Decisions | 02 Database Choice Discussion | Should we use Docker for PostgreSQL in development? | Yes
1-Decisions | 02 Database Choice Discussion | How to handle database seeding? | Yes
1-Decisions | 03 Ripwire Architecture Artifacts | Which ripwire version and command will be documented in the README? Answer: `npm run ripwire` (ripwire 0.5.0), see `docs/ripwire.md`. | Yes
2-Scaffold | 04 Database Design & Setup | PostgreSQL vs SQLite? → **PostgreSQL** (see task 02-database-choice-discussion.md) | Yes
2-Scaffold | 04 Database Design & Setup | Prisma as single source of truth? → yes; DBML dropped | Yes
2-Scaffold | 04 Database Design & Setup | How to handle database seeding? | Yes
2-Scaffold | 04 Database Design & Setup | Do we need indexes for this project scale? | Yes
2-Scaffold | 05 Next.js + Tailwind CSS + shadcn/ui Setup | Which shadcn/ui components do we need initially? | Yes
2-Scaffold | 05 Next.js + Tailwind CSS + shadcn/ui Setup | Should we use dark mode from the start? | Yes
2-Scaffold | 05 Next.js + Tailwind CSS + shadcn/ui Setup | Custom color palette or default shadcn colors? | Yes
2-Scaffold | 06 Backend Project Setup (Next.js Route Handlers & Services) | PostgreSQL vs SQLite for development? → PostgreSQL (task 02 decision) | Yes
2-Scaffold | 06 Backend Project Setup (Next.js Route Handlers & Services) | Which ORM to use? → Prisma | Yes
2-Scaffold | 06 Backend Project Setup (Next.js Route Handlers & Services) | Should we use a logger library (winston, pino)? | Yes
2-Scaffold | 07 TypeScript Strict Configuration | Should we enable `exactOptionalPropertyTypes`? | Yes
2-Scaffold | 07 TypeScript Strict Configuration | How to handle third-party library types? | Yes
2-Scaffold | 07 TypeScript Strict Configuration | Should we use `type` or `interface`? | Yes
2-Scaffold | 08 ESLint + Prettier Configuration | Should we use Biome instead of ESLint + Prettier? (faster) | Yes
2-Scaffold | 08 ESLint + Prettier Configuration | Which import sorting order do we prefer? | Yes
2-Scaffold | 08 ESLint + Prettier Configuration | Should we enforce strict TypeScript rules? | Yes
2-Scaffold | 09 Playwright E2E Testing | How to handle test data seeding? | Yes
2-Scaffold | 09 Playwright E2E Testing | Should we test on multiple browsers? | Yes
2-Scaffold | 09 Playwright E2E Testing | How to handle real-time test assertions? | Yes
2-Scaffold | 09 Playwright E2E Testing | Should we mock API calls or use real backend? | Yes
2-Scaffold | 10 GitHub Actions CI/CD Workflow | Should we deploy on merge to main? | Yes
2-Scaffold | 10 GitHub Actions CI/CD Workflow | Should we run E2E tests in CI from the start or only near Gate 4? | Yes
2-Scaffold | 10 GitHub Actions CI/CD Workflow | Can the ruleset enforce the docs-direct carve-out per path? | Yes
3-Features | 11 Backend API & Authentication | JWT vs session-based auth? → JWT in httpOnly cookie (kickoff) | Yes
3-Features | 11 Backend API & Authentication | Should we implement passwordless login? | No
3-Features | 11 Backend API & Authentication | How long should tokens be valid? | No
3-Features | 11 Backend API & Authentication | Express vs another framework? → no Express; Next.js route handlers (kickoff) | Yes
3-Features | 12 Frontend UI Development | React vs Vue vs Svelte? → React in Next.js (kickoff) | Yes
3-Features | 12 Frontend UI Development | Which CSS framework? → Tailwind + shadcn/ui (kickoff) | Yes
3-Features | 12 Frontend UI Development | State management approach? → custom useSyncExternalStore session store; TanStack Query not adopted (PR #24) | Yes
3-Features | 12 Frontend UI Development | Component library? → shadcn/ui (kickoff) | Yes
3-Features | 13 Patient View & Search | How to handle Polish characters in search? (ł, ż, ó) | No
3-Features | 13 Patient View & Search | Should we implement autocomplete for search? | No
3-Features | 13 Patient View & Search | What's the optimal page size for search results? | No
3-Features | 13 Patient View & Search | Should we cache search results? | No
3-Features | 14 Medical Notes with Visibility Control | Should notes support rich text or plain text only? | No
3-Features | 14 Medical Notes with Visibility Control | What's the character limit for notes? | No
3-Features | 14 Medical Notes with Visibility Control | Should we show edit history for notes? | No
3-Features | 14 Medical Notes with Visibility Control | How to handle note deletion (soft delete vs hard delete)? | No
3-Features | 15 Blockchain Access Logging | Which blockchain library to use? (Consider crypto-js for simplicity) | No
3-Features | 15 Blockchain Access Logging | How to handle blockchain size growth? | No
3-Features | 15 Blockchain Access Logging | Should we implement mining/proof-of-work? (Probably not needed) | No
3-Features | 15 Blockchain Access Logging | How to handle server downtime and sync recovery? | No
3-Features | 16 P2P Network Implementation | How to handle server startup order? | No
3-Features | 16 P2P Network Implementation | What's the sync interval for blockchain? | No
3-Features | 16 P2P Network Implementation | How to handle conflicting updates? | No
3-Features | 16 P2P Network Implementation | Should we implement encryption for P2P messages? | No
4-Integration | 17 User Roles & Access Control | How to handle organization-based access for primary care centre? Answered: primary care centre is the login role | Yes
4-Integration | 17 User Roles & Access Control | Should we implement audit logging for all access attempts? | No
4-Integration | 17 User Roles & Access Control | How to handle role changes (e.g., nurse becomes doctor)? | No
4-Integration | 17 User Roles & Access Control | Should we implement session timeout? | No
4-Integration | 18 Socket.io Broadcasting | Should we use Redis adapter for scaling? (open — single-pair demo works without it) | No
4-Integration | 18 Socket.io Broadcasting | How to handle socket authentication? (JWT session cookie verified at handshake + peer shared secret for P2P calls) | Yes
4-Integration | 18 Socket.io Broadcasting | What's the reconnection strategy? (socket.io-client auto-reconnect, 5 attempts, client-side note dedup on resync) | Yes
4-Integration | 18 Socket.io Broadcasting | Should we implement message acknowledgments? (open — current flow relies on client-side dedup instead) | No
5-Delivery | 19 Testing & Quality Assurance | Which testing framework to use? → Vitest (unit/integration) + Playwright (E2E), matching task 09. | Yes
5-Delivery | 19 Testing & Quality Assurance | How to set up test database? → Docker Postgres via `e2e/global-setup.ts`, migrated and seeded per run. | Yes
5-Delivery | 19 Testing & Quality Assurance | Should we implement E2E tests with Cypress? → No, Playwright was already chosen in task 09. | Yes
5-Delivery | 19 Testing & Quality Assurance | How to handle socket.io testing? → Two `next start` instances (3001/3002) with real Socket.io ports; cross-server delivery is asserted over a WebSocket client. | Yes
5-Delivery | 20 Documentation & README | Which screenshot tool to use? | No
5-Delivery | 20 Documentation & README | How detailed should API documentation be? → route-handler table in README | Yes
5-Delivery | 20 Documentation & README | Should we use a documentation generator? → no (shared types; kickoff) | Yes
5-Delivery | 20 Documentation & README | How to format meeting notes consistently? → `YYYY-MM-DD-<meeting-type>.md`; use the structure in [`docs/MEETING_TEMPLATE.md`](../MEETING_TEMPLATE.md) and keep raw transcripts in `docs/meetings/archive/`. | Yes
5-Delivery | 21 Presentation Preparation | Will we use slides or just live demo? | No
5-Delivery | 21 Presentation Preparation | Who presents which part? | No
5-Delivery | 21 Presentation Preparation | What's the backup if demo fails? | No
5-Delivery | 21 Presentation Preparation | How to handle unexpected questions? | No
Other | 22 Solana Repo Split and Toolchain | Does `anchor build` require platform tools (`cargo install --locked --git https://github.com/anza-xyz/platform-tools`)? | No
Other | 22 Solana Repo Split and Toolchain | Which devnet RPC provider for E2E? The public endpoint rate-limits under parallel tests | No
Other | 23 Freeze the Interface Contract | Does Anchor 1.2 use `declare_program!` or classic `declare_id!`? Confirm against installed docs before task 24 writes the scaffold | No
Other | 23 Freeze the Interface Contract | Is the event emission API still `emit!(AccessLogged {...})` in 1.x? | No
Other | 24 Solana Program Scaffold | Confirm whether Anchor 1.2 requires `declare_program!` with an IDL file, or classic `declare_id!` | No
Other | 24 Solana Program Scaffold | Does `anchor build` need platform tools (`cargo-build-sbf`) installed separately? | No
Other | 24 Solana Program Scaffold | Should the IDL be committed at scaffold time or after task 27? | No
Other | 25 Pure Hash Chain Module | Should `chain_head` use SHA-256 directly or a domain-separated variant? Direct SHA-256 matches the contract and keeps client and program identical | No
Other | 25 Pure Hash Chain Module | Should `verify_chain` live here or in a later task? Contract puts it here | No
Other | 26 Durable Outbox and Solana Flusher | Flush on write plus a periodic sweep, or a fixed timer? The former gives snappy demo behavior without hammering devnet | No
Other | 26 Durable Outbox and Solana Flusher | Retain pending events for how long before giving up? | No
Other | 26 Durable Outbox and Solana Flusher | Batch multiple events per transaction to save fees, at the cost of per-event atomicity? | No
Other | 27 Build the Anchor Program | Should `record_access` cap `event_count` or payload age? | No
Other | 27 Build the Anchor Program | Emit the full `AccessEvent` on-chain, or only the hash with detail in Postgres? | No
Other | 28 Devnet Deploy | Which devnet RPC provider for the app and E2E? | No
Other | 28 Devnet Deploy | Record the exact deploy command in the README so the deployment is reproducible? | No
Other | 29 Solana Program Tests | Coverage threshold for the Rust program? The TS side uses 70%; mirror it? | No
Other | 29 Solana Program Tests | Should the tamper test live in Rust, TypeScript, or both? Both proves client and program agree | No
Other | 30 Solana Client and Environment | Cache the head hash or read per request? Per request is simpler and current enough | No
Other | 30 Solana Client and Environment | Should health fail loudly when the program is missing, or degrade to `status: degraded`? | No
Other | 31 Remove the Homemade Blockchain | Keep the two-server demo or drop to one and reclaim the time? Recommendation: keep, it is the HA story | No
Other | 31 Remove the Homemade Blockchain | Should `AccessLog` rows exist for pending events, or only anchored ones? | No
Other | 32 Wire Flusher to the Solana Program | Flush immediately on write plus a periodic sweep, or on a fixed interval? | No
Other | 32 Wire Flusher to the Solana Program | What is acceptable pending lag before the demo looks wrong? | No
Other | 33 Patient Wallet Integration | Does consent need revoking? Revocation on-chain is a real design problem, likely out of scope | No
Other | 33 Patient Wallet Integration | Should patients read their own log entries directly from chain, bypassing the app? | No
Other | 34 Solana Verification UI | Should the chain panel be visible to staff too, or patients only? | No
Other | 34 Solana Verification UI | Poll for pending entries or rely on the socket? Socket is smoother if the flusher emits | No
Other | 35 E2E and Submission Disclosure | Do the devnet specs need a funded CI wallet, or should the demo account be a documented devnet address? | No
Other | 35 E2E and Submission Disclosure | Should the specs live in `e2e/solana/` as a separate directory? | No
Other | 36 Hackathon Documentation | Remove the course logbooks from the fork; keep `gruppkontrakt.md` and the meeting notes for honest provenance | Yes
Other | 36 Hackathon Documentation | Mermaid in markdown, or a rendered image? Mermaid renders on GitHub and stays current | No
Other | 37 Hackathon Submission and Decks | Target the University award explicitly, or let it follow from the work? | No
Other | 37 Hackathon Submission and Decks | Which track: Solana, or a general submission? Solana is a separate $100k pool | No
Other | 37 Hackathon Submission and Decks | Is the repo public? It must be, or `hackathon@colosseum.com` needs access | No